# Stochastic RCPSP — ADP Implementation

Personal reference document. Written for interview-day revision.

## Contents

- Setup — how the repo was created, PowerShell commands, base structure.

- Overview — gist of the project, motto, mission, interview signal.

- Theoretical Concepts — every concept underlying the project, revision-format.

- Code Walkthrough — file-by-file explanations. Grows as more files are added.

# 1. Setup

Factual record of how this repo was created from scratch.

## Environment

- Laptop: HPE Victus

- OS: Windows

- Shell: PowerShell (opened inside VS Code with Ctrl + backtick)

- Editor: VS Code

- Python: system Python 3

- External libraries so far: numpy only

## Step 1 — GitHub repo creation

- github.com → top-right “+” → New repository.

- Named the repo.

- Visibility: Public.

- Ticked “Add a README file” so the repo isn’t empty on first clone.

- “.gitignore” dropdown → chose “Python” — generates a template listing everything git should ignore.

What is .gitignore? A plain text file at the repo root that lists patterns git should not track. GitHub’s Python template covers virtual environment folders (venv/), compiled Python bytecode (__pycache__/, *.pyc), and editor junk. Anything matching a line here is skipped on git add / git commit.

Why it matters: without it, the venv/ folder — often hundreds of megabytes and specific to the OS — gets pushed to GitHub. .gitignore prevents that.

## Step 2 — Clone locally

Opened VS Code, then VS Code’s built-in terminal (Ctrl + backtick).

Navigated to the projects folder:

cd C:\Users\Harshan\Projects

Cloned:

git clone https://github.com/Harshan-14/<repo-name>.git
cd <repo-name>

Opened the folder as a VS Code workspace:

code .

The . means “current folder” — VS Code opens the directory as the project root.

## Step 3 — Folder structure

Inside the repo root, from PowerShell:

mkdir src
mkdir data
mkdir scripts
mkdir tests

Why these four: - src/ — importable project code - data/ — the paper’s problem instance data - scripts/ — runnable entry points - tests/ — sanity checks

## Step 4 — Package marker file

New-Item src\__init__.py -ItemType File

What is __init__.py? An empty file whose existence tells Python “this folder is an importable package.” Without it, from src.models import Task fails — Python won’t recognise src as importable. The file is empty; its presence is the signal.

## Step 5 — Requirements file

Created requirements.txt at the repo root:

numpy

What is requirements.txt? Plain text list of Python libraries the project needs. Anyone opening the repo can run pip install -r requirements.txt to install everything. Will be appended as new libraries appear.

## Step 6 — Virtual environment (optional but recommended)

Isolates project-specific libraries from the system Python — no version clashes between projects.

Create:

python -m venv venv

Activate (PowerShell may require a one-time policy change first):

Set-ExecutionPolicy -Scope CurrentUser -ExecutionPolicy RemoteSigned
venv\Scripts\Activate.ps1

Once activated, the prompt shows (venv) at the start. Install libraries:

pip install -r requirements.txt

## Step 7 — Sanity check

Verified imports work from the repo root:

python -c "from src.models import Task, Project, ProblemSpec; print('OK')"

Prints OK. Setup complete.

# 2. Overview

## The gist

A from-scratch implementation of an approximate dynamic programming (ADP) solution to the Stochastic Resource-Constrained Project Scheduling Problem (sRCPSP), based on a published operations research paper.

The problem in one paragraph. Several projects need to be scheduled. Each project is a chain of tasks. Every task must run on a specific lab, and only one task can occupy a lab at a time. Task outcomes — success/failure, duration, cost — are uncertain until the task runs. Each project has a reward that decays over time, meaning finishing quickly matters. You have to decide, at every moment, which tasks to start on which labs to maximize expected total reward.

Why this is hard. The exact problem has roughly 230 billion possible states — far beyond what standard dynamic programming can handle. The paper’s contribution is an ADP technique that uses simple heuristics to identify the small subset of states that reasonable policies actually visit (around 371,000 states), then runs Bellman iteration only on that subset. The resulting policy outperforms every pure heuristic in expected reward.

## Scope — Scope B

Reduced-surface build:

- One heuristic: Heuristic 1 — highest expected success probability at each decision point.

- One online decision method: barrier method (large-cost fallback for out-of-subset states).

- Full Bellman iteration over the heuristic-confined state space.

- Held-out validation on independent random realizations.

Deliberately excluded from Scope B: Heuristics 2 and 3, the guiding-heuristic online method, Section 7 extensions, and visualization polish. If time permits, these are added back.

## Motto

Understand deeply. Build correctly. Defend at any depth.

## Mission

Build one flagship project defensible at any level of technical probing in an interview. Previous rejections at JPM, Goldman, Amazon, and Thorogood happened at the final round — where the failure mode is technical depth, not communication. This project fills the gap other resume projects don’t: stochastic optimization, dynamic programming under uncertainty, reproducing a published research result.

## Signal to interviewers

- Comfort reading a research paper and shipping an end-to-end implementation.

- Working vocabulary in stochastic control — Bellman equations, cost-to-go, contraction mapping, Markov decision processes — the exact language used in JPM quant research, Goldman strats, and Amazon operations research.

- Empirical discipline — comparing an ADP policy against a pure-heuristic baseline on independent held-out data, not just training data.

- Judgment — scope-cutting to Scope B rather than shipping a partial, haphazard version.

# 3. Theoretical Concepts

Revision-format definitions. Each is written to be recalled and delivered in an interview in 2–3 sentences.

## 3.1 sRCPSP — Stochastic Resource-Constrained Project Scheduling Problem

Multiple projects need to be scheduled, each a sequence of tasks. Tasks compete for a small number of shared resources (labs). Every task’s success, duration, and cost are drawn from probability distributions — you commit to a decision before seeing the outcome. Goal: maximize expected total reward.

“Stochastic” — durations, costs, and even success/failure are random. “Resource-constrained” — one task at a time per lab.

## 3.2 Heuristic

A simple, rule-based decision policy that is not optimal but is fast and reasonable. Example (Heuristic 1): “at each decision point, start the task with the highest expected success probability.”

Two purposes: - Baseline to compare our final policy against. - State-space explorer — running the heuristic many times reveals which states reasonable policies actually visit. That set becomes our confined subset for Bellman iteration.

## 3.3 Markov Chain

A sequence of stochastic events where the probability of the next event depends only on the current state, not the full history. This is the Markov property.

In this project: within a single project, consecutive task outcomes are correlated via a Markov chain. If task 1 landed in realization 3 (“high success”), the distribution over task 2’s outcomes is different from what it would be if task 1 had landed in realization 1 (“failure”). We store this correlation as a transition matrix PM — column j is “given previous task landed in realization j, distribution over next task’s realizations.”

Cross-project independence: correlation is within a project only. Project 1’s outcomes tell you nothing about Project 2’s. Projects interact only through resource sharing.

## 3.4 Dynamic Programming (DP)

An optimization technique for sequential-decision problems, where each decision’s value depends on downstream decisions.

Structure: define a state that captures everything needed to decide from now onward; compute each state’s value by working backward from terminal states; use those values to select the best decision at each state.

Why it applies here: we make a sequence of scheduling decisions, each changing the state, and each with value depending on the future.

## 3.5 Approximate Dynamic Programming (ADP)

The full sRCPSP state space is around 230 billion states. Exact DP is infeasible.

ADP’s fix: approximate. Only compute values for a small, relevant subset of states. Handle the rest with fallback rules.

Our scheme: 1. Run heuristics to generate trajectories. 2. The set of visited states = our confined subset (~371k states). 3. Bellman iterate inside this subset. 4. Handle out-of-subset states with two approximation rules (concepts 3.10 and 3.11).

## 3.6 State, Decision, Transition

State (X): all information needed to decide from this point forward. - sᵢ — how far along project i is (which task is next). - zᵢ — which realization the last completed task of project i landed in (needed for Markov lookup). - Lⱼ — how long lab j has been busy (0 = idle). - t — current time.

Decision (U): for each project, a binary flag — start next task now, or don’t.

Transition: two steps. Apply the decision (advance sᵢ for started projects, occupy their labs). Then fast-forward to the next task completion — sample its realization from the Markov chain, update zᵢ, free the lab, advance t. Event-based, not clock-based.

## 3.7 Cost-to-go (J)

The expected future cost minus expected future reward from a given state until termination.

Written J(X). Interpretation: “if I’m in state X now and make optimal decisions from here forward, what’s my expected net cost?”

Sign convention: cost-minimization framing. Costs positive, rewards subtracted. Smaller J is better. Argmin, not argmax.

J* vs Ĵ*: J* is the truly optimal cost-to-go — unreachable on this problem. Ĵ* is our approximate cost-to-go from Bellman iteration on the confined subset. Everything downstream uses Ĵ*.

## 3.8 Bellman Iteration

The algorithm that computes cost-to-go values.

One iteration — for every state X in the confined subset:

Ĵ_new(X) = min over u of E[cost of u − reward from u + Ĵ_old(next state)]

- Minimization picks the best decision.

- Expectation averages over random realizations.

- Ĵ_old on the right is the current guess for downstream cost-to-go.

Repeat until Ĵ stops changing meaningfully. Paper’s stopping rule: max relative change < 1%. Converges in about 14 iterations.

Why does it converge? The Bellman operator is a contraction mapping — each application shrinks the error between the current estimate and the true optimum. By the Banach fixed-point theorem, a contraction has a unique fixed point that iteration converges to from any starting guess.

Interview one-liner: “Bellman iteration converges because the Bellman operator is a contraction mapping, which by Banach’s fixed-point theorem has a unique fixed point that iteration converges to from any starting guess.”

## 3.9 Confined State Space

The ~371k-state subset discovered by running heuristics many times. Everything outside this subset is treated as unreachable.

Why confine? Most of the 230 billion states are unreachable by any sensible policy (e.g., “all labs idle for 30 units”). Observing which states heuristics actually visit gives us a relevant, tractable subset.

Cost of confining: the subset is only as good as the heuristics that built it. If the optimal policy would visit a state the heuristics never touch, we can’t discover it. This is the algorithm’s fundamental blind spot — hence the paper’s three orthogonal heuristics (success / speed / reward). Scope B uses only H1, so this blind spot is larger for us.

## 3.10 Type 1 Approximation — Barrier Method (untried decisions)

Situation: evaluating decision u at state X. The next state X’ from some realization was never visited by any heuristic — not in the subset, no Ĵ value for it.

Type 1’s answer: assign X’ a large positive value (a barrier). When Bellman minimizes over u, decisions leading to X’ look terrible, and the algorithm rejects them.

Effect: the policy is conservative — biased toward staying inside the known subset.

Barrier calibration: must be much larger than the largest legitimate cost, but not so large it swamps useful signal from in-subset Ĵ values.

## 3.11 Type 2 Approximation — Renormalization (rare realizations)

Situation: evaluating decision u at state X. Most next-states are in the subset, but a few rare realizations lead outside.

Type 2’s answer: ignore the outside realizations, sum probabilities over the in-subset ones, and renormalize so they add to 1. Effectively pretend the rare outside outcomes don’t exist.

Effect: slightly biased if the ignored tail was high-cost, but the update stays tractable.

Difference from Type 1: Type 1 handles “the decision was never tried” (whole branch unknown). Type 2 handles “the decision was tried but this specific realization is rare” (branch known, one leaf isn’t). Two failure modes, two patches.

## 3.12 Online Decision-Making (Barrier Method)

After Bellman iteration converges, we have Ĵ* for every state in the subset. Deploy the policy on fresh scenarios.

At each decision point during a run:

u* = argmin over u of E[cost of u − reward + Ĵ*(next state)]

Same expression as during iteration, but now recording the decision achieving the minimum, not the minimum value.

If a realization steers us outside the subset: apply the barrier — treat the outside state as having a large Ĵ. This biases the current decision toward realizations that keep us inside.

Why safe to resume once back inside: Ĵ*(X) is a property of the state X, not the trajectory that led there. This is the Markov property of the state. Doesn’t matter if we arrived via the optimal policy or by wandering — Ĵ*(X) is the same. Resuming the optimal policy after re-entering the subset is valid.

## 3.13 Interview vocabulary checklist

Precise terms to use:

- Stochastic dynamic programming

- Markov decision process (MDP)

- Cost-to-go function

- Bellman equation / Bellman operator

- Contraction mapping / Banach fixed-point theorem

- Approximate dynamic programming

- Heuristic-confined state space

- Type 1 (barrier) and Type 2 (renormalization) cost-to-go approximations

- Online policy execution

- Held-out validation

# 4. Code Walkthrough

Every file we build gets a subsection here. Grows as we go.

## 4.1 src/models.py — Data Model

### What this file is for

Purely a data model. Defines the shape of the problem instance using Python dataclasses. No logic — no simulation, no probability sampling, no scheduling — just containers.

The schema. Every downstream module reads objects defined here.

### Structure — three nested classes

Task — the smallest unit. - task_id — human-readable name from the paper (e.g. “I1”, “P3”). - lab — which lab this task runs on. - realizations — tuple of possible outcomes. Each realization is a (result, duration, cost) triple. - num_realizations() — how many possible outcomes this task has.

Project — a chain of tasks + reward parameters + Markov chain data. - project_id - tasks — tuple of Task objects, in order. - R0, alpha, PD, beta — reward function parameters. - PI — initial probability vector for the first task. - PM — tuple of transition matrices, one between each consecutive pair of tasks. - num_tasks()

ProblemSpec — the whole problem. - projects — tuple of Project objects. - num_labs — total resources available. - num_projects()

### Key design decisions

1. frozen=True on every dataclass. Once built, instances can never be mutated. Kills a class of bug where a stray line silently rebinds a probability matrix mid-simulation, corrupting downstream results without any error. Immutability = safety.

2. PM matrix shape convention. Each PM[n] matrix has shape (next_task_realizations, current_task_realizations). Meaning: columns index the “given” (previous task’s realization), rows index the “outcome” (next task’s realization).

Column j of PM[n] is a probability vector summing to 1 — the distribution over next task’s realizations given previous task landed in realization j.

This convention must not be inverted. Every downstream file reads columns of PM matrices. Flip rows and columns → probabilities become nonsense while everything runs without errors → silent corruption.

3. @property decorators removed. Access is method-style with parentheses: task.num_realizations(), not task.num_realizations. Consistent across all three classes.

4. No I/O, no logic. Only defines structures. Doesn’t populate them. That’s data/problem_spec.py (still to be built).

### How other files will use it

from src.models import ProblemSpec
from data.problem_spec import build_spec

spec = build_spec()             # a ProblemSpec
project_1 = spec.projects[0]    # first Project
task_1 = project_1.tasks[0]     # first Task
task_1.realizations             # tuple of (result, duration, cost)
project_1.PM[0]                 # transition matrix task 0 → task 1
project_1.PM[0][:, 2]           # distribution over task 1's outcomes given task 0 landed in realization 2

### What this file does not do

- No probability sampling — that’s markov.py.

- No state representation — that’s state.py.

- No transition logic — that’s transitions.py.

- No scheduling decisions — that’s heuristic.py.

- No I/O — data is populated by data/problem_spec.py.

### Interview one-liner

“models.py defines frozen dataclasses for the problem structure — Task, Project, ProblemSpec. Frozen guarantees the problem instance can’t be mutated mid-run. The main design decision is the shape convention on the Markov transition matrices: columns index the previous task’s realization, rows index the next task’s realization. Every downstream module reads columns of these matrices, so getting the convention wrong would silently corrupt every simulation.”

4.2 data/problem_spec.py — Paper Instance

What this file is for

Populates the empty schema in models.py with the paper's Section 6 instance: 5 projects, 17 tasks, 2 labs, α = 0.235, β = 0. Called once at pipeline startup via build_spec().

Uses Path B data: shapes and correlations match the paper's qualitative structure, exact Table 1 numbers are placeholders. Swapping in the paper's literal values later touches only this file.

Structure

- Two module-level templates: _PI_DEFAULT (initial probability vector) and _PM_DEFAULT (transition matrix).

- Five per-project builders (_build_project_1 through _build_project_5). Each function contains all the data for one project.

- One validator _validate — checks PI sums, PM column sums, and shape consistency.

- One public entry point build_spec — composes the projects, runs validation, returns the ProblemSpec.

Key design decisions

- Uniform 3 realizations per task. Every task has (fail, moderate, high). Every PM is shape 3×3. Simplifies the pipeline and keeps the file scannable.

- Success-persistence Markov transitions. Previous failure → more likely to fail; previous success → more likely to succeed. Without this correlation, the zᵢ component of the state vector would be dead weight.

- .copy() on template reuse. Frozen dataclass prevents reassignment of numpy fields but not in-place mutation of the array itself. Copying at construction time isolates each project's data.

- Load-time validation via assertions. Data-entry typos raise on import with a precise error message (project, matrix, column). Prevents silent corruption during long Bellman runs.

What this file does not do

- No probability sampling — that's markov.py.

- No state, decisions, or transitions — those are state.py and transitions.py.

- No I/O to disk — the paper instance is hardcoded Python.

Interview one-liner

"problem_spec.py populates the schema with the paper's 5-project instance. Templates for PI and PM keep the code compact; each project sits in its own builder function. A load-time validator asserts every PI sums to 1, every PM column sums to 1, and shapes match realization counts — so any data-entry typo fails loudly on import rather than silently corrupting downstream simulation."

src/state.py — State Representation

What this file is for

Defines the immutable snapshot of the system at a decision point in the simulation. A State captures everything needed to determine future evolution — used both for stepping the simulator forward and as a hash key inside the confined state subset during Bellman iteration.

Structure

- Decision — type alias for a binary vector (δ₁, ..., δ_M).

- State — frozen dataclass with six fields: next_task, z, lab_owner, lab_realization, lab_time_in_use, t.

- initial_state(spec) — returns the t=0 state.

- Query helpers: project_running, project_done, lab_free, is_terminal. All are pure queries; none mutate.

Field semantics

- next_task[i] — next unstarted task index of project i (0-indexed).

- z[i] — realization index of project i's most recently completed task, or -1 if none.

- lab_owner[j] — project id currently running on lab j (1-indexed); 0 if lab is free.

- lab_realization[j] — sampled realization index for the in-progress task; -1 if free.

- lab_time_in_use[j] — how long lab j has been running its current task; 0 if free. Corresponds to the paper's L_j.

- t — current simulation time.

What this file does not do

- No decision enumeration or state transitions — those go in transitions.py.

- No sampling — that's markov.py.

- No reward or cost accounting — that's reward.py.

Interview one-liner

"state.py defines a frozen dataclass with all-tuple fields, so states are hashable and usable as dict keys during Bellman iteration. The state carries per-project position and last realization, per-lab occupancy, sampled-but-not-yet-applied realization, and elapsed time — enough to fully determine future evolution. lab_realization is in state because we sample at task start (to know duration) but apply the effect at completion, and the gap between those two events has to be representable."

4.4 src/markov.py — Realization Sampling

What this file is for

The single point in the codebase where task outcomes are drawn from the Markov chain. Every other module is deterministic given its inputs; only this file consults the RNG for realization sampling.

Structure

One function: sample_realization(rng, project, task_idx, prev_realization) → int. Returns the 0-based realization index. Caller looks up the (result, duration, cost) tuple.

Branching

- task_idx == 0 → sample from project.PI (initial distribution).

- task_idx > 0 → sample from column prev_realization of project.PM[task_idx - 1].

Key design decisions

- RNG passed in, not created inside. Same seed at the top of the pipeline → identical trajectory. Reproducibility is a whole-pipeline property. Debugging a specific rare event is possible because it's deterministic.

- Defensive asserts on inputs. task_idx in range; prev_realization in the previous task's realization range (only checked when task_idx > 0). A sentinel -1 leaked in for task_idx > 0 fails loudly with a message naming the project and task.

- Return int, not numpy.int64. Cleaner for State tuple hashing downstream; no cross-type comparison surprises.

- No probability-sum re-validation. problem_spec.py guarantees the invariant at load time. Trust it here.

What this file does not do

- No RNG construction (caller manages that).

- No tuple lookup — that's a one-liner in the caller.

- No state transitions or scheduling — those live in transitions.py.

Interview one-liner

"markov.py samples task realizations by picking the right column of the project's transition matrix — column prev_realization of PM[task_idx - 1] for follow-on tasks, or PI for the first task. Randomness comes from a numpy.Generator passed in by the caller, so reproducibility is a whole-pipeline property. Return type is Python int for clean state-tuple hashing."

src/transitions.py

The only module that produces new States from old ones. Everything else reads state; this file writes it.

What lives in this file

Three pure functions, cleanly separated by concern:

- enumerate_decisions(state, spec) — lists all legal decisions from the current state. No RNG, deterministic.

- apply_decision(state, decision, spec, rng) — starts the tasks in the decision on their required labs, samples each task's realization at the moment it begins. Does not advance the clock.

- advance_to_next_event(state, spec) — finds the busy lab with minimum remaining time, moves the clock by that Δt, frees any lab(s) that finish exactly then, records the sampled realization into z[i], and returns both the new state and a tuple of completion events for reward.py to consume.

Plus two type aliases: Decision (sorted tuple of (project_id, lab_id) pairs) and CompletedEvent ((project_id, task_idx, realization_idx, completion_time)).

Design decisions worth flagging

1. next_task[i] increments at task START, not completion.
So next_task[i] = number of tasks started for project i. The in-flight task on lab j is at index next_task[lab_owner[j]-1] - 1. Alternative was storing per-lab task indices, but that duplicates information the state already carries via lab_owner — cleaner to increment at start.

2. Empty decision () is legal only when at least one lab is busy.
If all labs are free and we accept the empty decision, advance_to_next_event has nothing to advance to and time freezes forever. Forbidding empty when all labs are free eliminates this soft-lock while preserving the barrier method's future ability to strategically wait (which only matters when labs are busy).

3. Eligibility rule is simple because tasks fix their lab.
Project i is eligible for lab j iff it has unstarted work, is not already running elsewhere, and its next task's required lab equals j. Since each task fixes its lab, a project is eligible for at most one lab at any moment — the Cartesian product over free labs cannot accidentally schedule the same project twice.

4. Sampling at task START, applying effect at task COMPLETION.
lab_realization[j] gets populated on apply_decision — this is when we roll the dice against PI or PM and lock in which realization row (result, duration, cost) this task will land on. But z[i] (the state's memory of the last completed realization for project i) only gets updated on advance_to_next_event, at the exact moment the task finishes. This matches the paper's event-based two-step transition and preserves the Markov property: PM lookups in apply_decision read z[i], which reflects only truly completed history.

5. advance_to_next_event returns (new_state, completed_events).
An explicit hand-off rather than making reward.py diff two states to figure out what happened. Each event carries (project_id, task_idx, realization_idx, completion_time) — everything reward.py needs to charge cost and credit reward.

6. Simultaneous completions handled in one call.
If Δt frees two labs at once, both are freed in the same advance_to_next_event return. The next decision epoch then enumerates with multiple free labs. No arbitrary tie-breaking, no lost events.

7. NO special failure handling.
This project uses Path B representative data. _PM_DEFAULT does not zero the failure column, so recovery from failure is modeled — a failed task does not kill the project. This is a documented deviation from the paper's Table 1 semantics, and reward.py will handle any earnings penalty for failed realizations. Documenting because it's the kind of thing an interviewer will drill on.

8. Decision as sorted tuple.
Canonical form makes decisions hashable and equality-comparable for free. Every enumeration result is sorted, both internally and across the returned list.

Interview one-liner

"transitions.py holds the state machine. Three functions: enumerate the legal decisions, apply a chosen decision by starting tasks and sampling realizations, then advance the clock to the next completion event. The key design decision is separating the two-step transition — sample at start, apply the effect at completion — because that's what preserves the Markov property of the state and lets the Bellman recursion work later. It's also the only module that produces new States; everything else reads state."

src/reward.py

Cost and reward accounting. Consumes completion events produced by advance_to_next_event and turns each event into a (cost, reward) pair that the simulator accumulates into J.

What lives in this file

Three public functions plus one private helper:

- task_cost(event, spec) — pulls the cost from the completed task's realization triple (result, duration, cost). Always applicable.

- project_reward(project_id, completion_time, spec) — piecewise exponential reward function R_i(k). Handles the pre-deadline and post-deadline branches.

- accrue(event, state_after, spec) — the single entry point the simulator calls. Returns (cost, reward) for one completion event. Reward is zero unless the event finishes the project's last task.

- _is_project_complete(project_id, state_after, spec) — private helper. True only when project has no more tasks to start AND is not currently occupying any lab.

Design decisions worth flagging

1. Cost-minimization framing.
J = accumulated_cost − accumulated_reward. Smaller J means larger expected profit. The accrue function returns cost and reward separately, and the simulator's convention is J += cost − reward per event. This sign convention is why the paper's cost-to-go values are large negatives — they represent large expected profits. Getting this backwards is the sign bug that Claude caught in the earlier phase-3 checkpoint.

2. Both cost and reward accrue at task COMPLETION.
The paper is ambiguous about whether task cost is charged at start or at completion. Charging both at completion keeps this file focused on one event type and makes advance_to_next_event's output tuple the sole reward-computation trigger. Splitting cost across start events would spread accrual logic between apply_decision and reward.py — more surface area, no benefit.

3. Reward function is piecewise exponential with a deadline.

- Pre-deadline (k ≤ PD): R(k) = R0 · exp(−α · k).

- Post-deadline (k > PD): R(k) = R0 · exp(−α · PD − β · (k − PD)).

Path B data has β = 0, so the post-deadline branch degenerates to a flat R0 · exp(−α · PD) — no additional penalty for slipping past the deadline. The piecewise form is kept in the code so the module remains correct if we ever swap in data with β > 0. The two branches are continuous at k = PD regardless of β.

4. Path B: no failure gating on completion reward.
This is the key deviation from the paper's original semantics. In the paper, a "fail" realization zeroes out the failure column of the next PM and effectively terminates the project — the project earns no completion reward because it never completes. In Path B, PMs allow recovery from failure and all tasks are attempted, so we take the consistent position: any project that finishes all its tasks earns its completion reward, regardless of individual realization results. Documented explicitly (test 10 guards this) because interviewers will drill on it.

5. Completion check needs both next_task and lab_owner.
Because next_task[i] increments at task start (not completion), next_task[i] == num_tasks(i) alone only proves the last task has been started — it may still be running. The correct check adds project_id not in state_after.lab_owner. Missing the second condition would credit reward before the last task actually finishes.

6. Per-event interface, no batch wrapper.
accrue handles one event at a time. The simulator iterates over completed_events returned by advance_to_next_event and accumulates J itself. This keeps reward.py stateless and makes simultaneous completions fall out naturally — the loop calls accrue per event using the same state_after, and each event's completion check is independent.